## Sheet1
Task Name | Assignee | Task Status | Expected time to finish | Actual time to finish
MCAL_TIMER_DESIGN | Bassel Yasser | done | 1 hour | 30 min
MCAL_TIMER_Implementation | Bassel Yasser | done | 1 hour | 45 min
MCAL_TIMER_Testing | Bassel Yasser | done | 30 mins | 20 mins
MCAL_EXTINT_Design | Arafa Arafa | done | 1.30 hour | 30 mins
MCAL_EXTINT_Implemetation | Arafa Arafa | done | 1 hour | 45 mins
MCAL_EXTINT_Testing | Arafa Arafa | done | 30 mins | 20 mins
HAL_BUTTON_Module | Arafa Arafa | done | 1 hour | 30 mins
MCAL_DIO_Design | Youssef Abbas | done | 1.30 hour | 1 hour
MCAL_DIO_Implemetation | Youssef Abbas | done | 1.15 hour | 50 mins
MCAL_DIO_Testing | Youssef Abbas | done | 15 mins | 30 mins
HAL_Button_Module | Youssef Abbas | done | 15 mins | 30 mins
SERVICE_SOS_Design | All Teams | done | 2.30 hour | 3 hour
SERVICE_SOS_Implementation | Mahmoud Sarhan | done | 2 hours | 3.30 hours
SERVICE_SOS_Testing | Mahmoud Sarhan | done | 1 hour | 1.30 hour
APPLICATION | Mahmoud Sarhan | done | 45 mins | 30 mins